## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Harrison | Daudi | Madison | Osama | Sung | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task (in days) | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | Totals
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 2 |  | 2 | 2 | 0 | 0 | 0 | 0 | 2
|  | Design architecture | Project Manager | Harrison | 2 |  | 1 |  | 2
| Documentation |  |  |  |  | 13 |  | 1.75 | 2.1 | 0 | 0 | 0 | 0 | 2.1
|  | Project Charter | Project Manager | Harrison | 1 |  | 0.25 |  | 0.25
|  | Release Plan | Project Manager | Harrison | 0.5
|  | Requirements Document | Project Manager, Requirements Engineer | Harrison | 1 |  | 0.25 |  | 0.25
|  | Project Plan | Project Manager, Developers | Harrison | 2 |  | 0.25 |  | 0.25
|  | Architecture Document | Architect | Harrison | 2
|  | Test Report | Tester | TBA
|  | Investigate Form Builder Libraries (Formik) | Architect | Harrison | 0.5 |  | 0.25 |  | 0.25
|  | Choose Component Library (Material UI) | Project Manager, UX | Harrison | 0.5 |  | 0.25 |  | 0.25
|  | Determine/ Integrate Front End Testing Framework (Jest) | Architect | Harrison | 1 |  | 0.25 |  | 0.25
|  | Technical Prototype | UX/ Designer, Project Manager, Architect | Harrison | 2
|  | Determine Security Scan Software (Black Duck, NPM Audit) | Project Manger, Architect | Harrison | 0.5 |  | 0.25 |  | 0.25
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | TBA | 2
Coding
Iteration 1: | Development |  |  |  |  | 25 |  | 11.5 | 8.5 | 5 | 4 | 4 | 4 | 25.5
|  | Determine technology needs | Project Manager | Harrison | 1 |  | 0.25 |  | 0.25
Start |  | Research and learn new language and environment | Developer | Daudi, Madison, Sungho, Osama | 4 |  | 4 |  | 1 | 4 | 4 | 4 | 4
2020-02-17 |  | Setup React App | Developer | Harrison | 1 |  | 0.5 |  | 0.5
|  | Setup Express Server | Developer | Harrison | 1 |  | 0.5 |  | 0.5
End |  | Setup MySQL | Developer | Harrison | 1 |  | 0.5 |  | 0.5
2020-03-02 |  | Create Base Login Page | Developer | Harrison | 1 |  | 1 |  | 1
|  | Login Page Validation (email, password) | Developer | Harrison | 2 |  | 0.5 |  | 0.5
|  | Create Home Page Route | Developer | Harrison | 1 |  | 0.25 |  | 0.25
|  | Create Sign Up Page (first, last, email, username, password) | Developer | Harrison | 2 |  | 0.5 |  | 0.5
|  | Sign Up Page Validation | Developer | Harrison | 1 |  | 0.25 |  | 0.25
|  | Login Page Validation Errors | Developer | Harrison | 2 |  | 0.25 |  | 0.25
|  | Login Page Input Fields and Button (Formik) | Developer | Harrison | 1 |  | 1 |  | 1
|  | Add Styling to Login Page (Commerce Bank Theme) | Developer | Harrison, Daudi | 2 |  | 1 |  | 1 | 1
|  | Login dataflow (UI -> Server -> DB) | Developer | Harrison | 5 |  | 1 |  | 1
| Analysis |  |  |  |  | 4.5 |  | 1.75 | 1 | 1 | 1 | 0 | 0 | 3
|  | System Testing | Tester | Madison, Daudi | 1 |  | 1 |  |  | 1 | 1
|  | Versioning (features and defects) | Project Manager | Harrison | 0.5 |  | 0.25 |  | 0.25
|  | Bug fix as required | Tester, Developer | Harrison | 2 |  | 0.25 |  | 0.25
|  | Evaluate needs for next iteration | Project Manager | Harrison | 1 |  | 0.25 |  | 0.25
Iteration 2: | Design |  |  |  |  | 3.5
|  | Implement any design changes | Project Manager | Harrison | 1
|  | Risk analysis | Project Manager | Harrison | 0.5
|  | Create UI For Home Screen/ Balances | UX/ Designer, Project Manager | Harrison | 2
Start | Development |  |  |  |  | 12
2020-03-02 |  | Review requirements | Developer | Daudi, Madison, Sungho, Osama | 1
|  | Determine Data Grid to Use (Dev Express) | Project Manger, UX | Harrison | 0.5
|  | Create Account Balance Components( Home Page) | Developer | Harrison, Daudi | 3
End |  | Create logic to find balance and feed data to balance component | Developer | Harrison | 2
2020-03-16 |  | Create Notification Center on Home Page | Developer | Harrison | 2
|  | Routes to navigate to each Balance Page | Developer | Osama | 0.5
|  | Create Checking Page | Developer | Sung | 0.5
|  | Create Savings Page | Developer | Madison | 0.5
|  | Unit Testing | Developer | Harrison, Daudi, Madison, Sungho, Osama | 2
| Analysis |  |  |  |  | 4
|  | System Testing | Tester | Madison, Sung, Osama | 1
|  | Versioning (features and defects) | Project Manger | Harrison | 1
|  | Bug fix as required | Tester, Developer | Harrison, Daudi, Madison, Sungho, Osama | 1
|  | Evaluate needs for next iteration | Project Manager | Harrison | 1
Iteration 3: | Design
|  | Implement any design changes | Project Manager | Harrison | 1
|  | Risk analysis | Project Manager | Harrison | 0.5
Start |  | Create UI Design for Nofication Messages | UX/ Designer, Project Manager | Harrison | 1
2020-03-16 |  | Create UI Design for Nofication Tool | UX/ Designer, Project Manager | Harrison | 1
Development
End |  | Review requirements | Developer | Daudi, Madison, Sungho, Osama
2020-04-06 |  | Implement Data Grid for Checking Account Page | Developer
|  | Implement Data Grid for Saving Account Page | Developer
|  | Add Styling to Home, Checking, Savings Pages (Commerce Bank Theme) | Developer
|  | Ability to Export Data from Grid into CSV (React CSV) | Developer
|  | Add Filtering and Sorting to Grid | Developer
Analysis
|  | Acceptance Testing | Tester, Project Manager | Harrison | 1.5
|  | Security Scanning and Package Audit (NPM, Black Duck) | Project Manager | Harrison | 1
|  | Versioning (features and defects) | Project Manger | Harrison | 1
|  | Bug fix as required | Tester, Developer
Iteration 4: | Design
|  | Implement any design changes | Project Manager | Harrison | 1
|  | Risk analysis | Project Manager | Harrison | 0.5
Start
2020-04-06
Development
End |  | Review requirements | Developer | Daudi, Madison, Sungho, Osama
2020-04-20 |  | Ability to Add a Transaction to Savings and Checking Account Pages | Developer
|  | Create Notifcation Rules | Developer
|  | Create Nofications Component | Developer
|  | Ability to Remove Notification From Home Screen | Developer
|  | Unit Testing | Developer
Analysis
|  | Acceptance Testing | Tester, Project Manager | Harrison | 1.5
|  | Security Scanning and Package Audit (NPM, Black Duck) | Project Manager | Harrison | 0.5
|  | Versioning (features and defects) | Project Manger | Harrison | 0.5
|  | Bug fix as required | Tester, Developer
Iteration 5: | Design
|  | Implement any design changes | Project Manager | Harrison | 2
|  | Risk analysis | Project Manager | Harrison | 0.5
Start
2020-04-20
Development
End |  | Review requirements | Developer | Daudi, Madison, Sungho, Osama
2020-05-04 |  | Show Notification by Priority on Home Page | Developer
|  | Create Notification Add, Edit, Delete Logic | Developer
|  | Add Styling for Notifications(Commerce Bank Theme) | Developer
|  | Add User Session (Stretch) | Developer
|  | Unit Testing | Developer
Analysis
|  | Acceptance Testing | Tester, Project Manager | Harrison | 1.5
|  | Security Scanning and Package Audit (NPM, Black Duck) | Project Manager | Harrison | 0.5
|  | Versioning (features and defects) | Project Manger | Harrison | 0.5
|  | Bug fix as required | Tester, Developer